## Stage Approvals
Project Stage Gate Review Checklist and Record
|  | Project: | Multi Level Oil Indicator
|  | Date Updated: | 2025-03-01
|  | Updated By: | Rick Ales
© 2024 R. Ales Consultng LLC
|  | Form ENG-034.A | Reviewed By | Reviewed By | Reviewed By | Reviewed By | Reviewed By | Reviewed By
Project Stage | Date of Review | Stage Status | Rick Ales, Project Manager | Enter Name, Title | Enter Name, Title | Enter Name, Title | Enter Name, Title | Enter Name, Title
SG1: Assess
SG2: Design
SG3: Develop
SG4: Validate and Verify
SG5 Release
SG6: Produce

## SG1 Assess
Assess Stage
Review Task | Status | Comment
Project Feasibility Assessment (Technology & Cost) | Not Applicable
ENG-037.x Project Charter | Approved
Product Requirements Definition (PRD) Approved and Signed by Customer | Approved
Project Customer Quote from Marketing | Not Applicable
Review of Proposed Project Schedule Requirements | Approved
Stage Gate Exit Approval Status | Approved
Assess Phase Milestones
Assess Tasks (From project plan) | % Complete

## SG2 Design
Design Stage finish by 5/5/2022
Review Task | Status | Comment
Review of Deliverables
Preliminary Design Document(s)
Test Requirement Specification (TRS)
Design Failure Mode Effects Analysis (DFMEA)
Approved Project-Specific Hardware Design Checklist
Approved Project-Specific Firmware / Software Checklist
Design Review Meeting Held
Project Continuation Feasibility
Review of Project Schedule
Marketing Review
Design for Manufacturability (DFM)
Stage Gate Exit Approval Status
Design Phase Milestones
Design Tasks (From project plan) | % Complete

## SG3 Develop
Develop Stage
Review Task | Status | Comment
Detailed Design Document(s)
o Final Schematic |  | TBD Kurtis
o PCB Layout |  | No Change
o PCB Gerber Files |  | No Change
SAGE Bill of Materials (BOM) and all other items from HW, FW, SW Checklists |  | TBD Kurtis
Firmware Source Code Review
Qualification Test Plan (QTP
Review of Project Schedule
Marketing Review |  | T6 issue Temp 55v70
Design for Manufacturability (DFM) |  | No Change
Stage Gate Exit Approval Status
Develop Phase Milestones
Develop Tasks (From project plan) | % Complete

## SG4 Validate and Verify
Validate and Verify Stage
Review Task | Status | Comment
Review of Deliverables
Prototype and Pilot Units Review
Qualification Test Plan (QTP) Results
Regulatory Certification Reseults
Review of Project Schedule
Marketing Review (Cost Target Achievement, etc)
Production Process Readiness Review
Design for Manufacturability (DFM)
Stage Gate Exit Approval Status
Develop Phase Milestones
Develop Tasks (From project plan) | % Complete

## SG5 Release
Release Stage
Review Task | Status | Comment
ECC Review and Signoff
All Documentation Release to the Controlled Document Vault
Review of Project Schedule
Marketing Review
Stage Gate Exit Approval Status
Release Phase Milestones
Release Tasks (From project plan) | % Complete

## SG6 Produce
Produce Stage
Review Task | Status | Comment
First Articles Inspection Record - As Required
Production Part Approval Process (PPAP) - As Required
Available for Production Level Shipment
Review of Project Lessons Learned (Post-Mortem)
Marketing Review
Decision on Project Closure
Stage Gate Exit Approval Status
Produce Phase Milestones
Produce Tasks (From project plan) | % Complete

## Setup
Stage Status
Status | Description
Approved | Stage is approved
Conditional Approval | Stage is conditionally approved
Disapproved | Stage is disapproved for Reissue
Cancelled | Project is Cancelled
Stage Not Required | Tailored Project Stage Not Applicable
Hold | Project is put on Hold
Status
Status | Description
Approved | Deliverable/task meets requirements and is approved
Conditional Approval | Deliverable/Task will be approved upon task condition satifactoryly being closed
Disapproved | Deliverable/Task does not meet requirements and is disapproved
Not Applicable | Deliverable/Task is not requqired for this project